## Resource Allocation
|  | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
Utilization | Resource | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
100% | Andreas | 2 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100% | Mareike | 6 | 5.75 | 5.25 | 5.25 | 5.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100% | Tom | 4 | 1.5 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100% | Tu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100% | Sebastian | 5.5 | 5.5 | 5 | 4.5 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Days Remaining | 17.5 | 13.75 | 11.75 | 10.75 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Burn Down
Priority | Description | Owner | Deliverable | Bug ID | Postponed | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
25 | Tabellendarstellung | Sebastian |  |  |  | 1: 1; 2: 1; 3: 1; 4: 0.5; 5: 0.5
25 | Registrierung | Mareike |  |  |  | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Notification Daemon | Sebastian |  |  |  | 1: 3; 2: 3; 3: 3; 4: 3; 5: 3
25 | Menü | Sebastian |  |  |  | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Hochladen eines Bildes | Andreas
10 | Ändern der Daten | Andreas |  |  |  | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Notifications auswählbar machen | Andreas |  |  |  | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | Favoriten zurücksetzen | Tom |  |  |  | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Fix async Timeout SMS | Sebastian | bar: 1 to 5
2 | Fix Datepicker Bug | Andreas |  |  |  | 1: 0.5; 2: 0; 3: 0; 4: 0; 5: 0
1 | Hinweise bei der Registrierung | Tom |  |  |  | 1: 0.5; 2: 0.5; 3: 0.5; 4: 0.5; 5: 0.5
2 | Flashingnachticht TourCreate | Tom |  |  |  | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Fix Timer Bugs | Andreas |  |  |  | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Redirect Telefonbestellung Links | Tom |  |  |  | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Tourseite anpassen | Tom |  |  |  | 1: 2; 2: 1; 3: 0.5; 4: 0.5; 5: 0.5
30 | Doku (alle) |  |  |  |  | 1: 5; 2: 5; 3: 5; 4: 5; 5: 5
4 | Automatisierte Buchung | Mareike |  |  |  | 1: 5.5; 2: 5.25; 3: 5.25; 4: 5.25; 5: 5.25

## Release Burn Down
Sprint | Progress | Scope Change

## Actual Allocation
|  | Over/(Under) | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
Resource | Max Days | Commited | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Andreas | 0 | 0 | 2 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mareike | 0 | 0 | 6 | 5.75 | 5.25 | 5.25 | 5.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tom | 0 | 0 | 4 | 1.5 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sebastian | 0 | 0 | 5.5 | 5.5 | 5 | 4.5 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Days Remaining |  |  | 17.5 | 13.75 | 11.75 | 10.75 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint Information
Sprint Length | 11
Work Hours in Day | 1 | <- Leave at 1 if work estimates for tasks on "Burn Down" worksheet are in days
Do not modify anything below this line!!!!
Number Tasks | 17
Desired Trend | 17.5 | 15.9091 | 14.3182 | 12.7273 | 11.1364 | 9.5455 | 7.9545 | 6.3636 | 4.7727 | 3.1818 | 1.5909 | 0
Remaining Avail | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Postponed | Yes | No
Individual Base | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Release Sprint | #DIV/0! | Release at End of Sprint ?
Upper Formula | 0 | 0
Lower Formula | 0 | 0
Upper Trend
Lower Trend
Chart Name | Burndown

## Instructions
May 9, 2008
Changes to this version:
1. Added conditional formatting to cross out tasks that had a "0" for hours remaining the most recently used column on the Burndown worksheet.
January 23, 2008
Changes to this version:
1. Fixed a problem on "Actual Allocation" sheet that would cause errors if rows were deleted from the "Resource Allocation" sheet.
2. The burndown chart title updates automatically to the filename of the workbook.
August 5, 2007
Changes to this version:
1. Added Release Burndown tab
June 15, 2007
Changes to this version:
1. Upwards compatible with Excel 2007
2. Resources can be scheduled to be allocated at less that 100% to the sprint being tracked
2. Added "Actual Allocation" worksheet to easily see when resources are less than 100% allocated to the sprint being tracked what their actual allocation is (the "Resource Allocation" worksheet presents a "normalized" view (i.e. if they WERE 100% allocated).
March 2, 2006
Changes in this version:
1. Postponing a task no longer removes it from burn down tracking. Plus side is you get a better picture of what happened during all phases of the sprint. Down side is you'll need to fill in 0's for time remaining of postponed tasks.
2. Added filtering to task owner column. Makes it easy to see only those tasks for a given owner
3. Added ability to track tasks by hours. Go to the "Sprint Information" worksheet and follow the instruction there
4. Added ability to assign utilization to each resource. Click the plus sign (+) at the top of column B on the "Resource Allocation" worksheet to assign utilization for each resource.
- Clay
Instructions to use template follow....
I created this template to assist in sprint burn down tracking and thought others might find it useful.
Features include:
1. Easy identification of over/under allocated resources (before and during a sprint)
2. Extensive use of conditional formatting to convey important information
3. A Burn Down chart (with desired trend line)
4. Use of drop downs to aid in data entry
5. Filtering to easily find all tasks for a given owner
6. And of course there’s more…
You can download a zip file of the template and a sample workbook using it at http://www.geocities.com/clayvv/BurndownTracking.zip.
One thing to note is that the template only uses formulas - no macros are used. So it should be safe for use in any computing environment. This does place some limits on what can be done, but macros can also be misused and frankly I don’t trust macros coming from an “unknown” source.
Steps to use:
1. Create a new workbook using “Sprint Burndown.xlt” as the template
2. Fill in the names of the people on your team on the 1st worksheet, “Resource Allocation” (You’ll probably want these in alpha sort order, but this is not required)
3. Delete the rows containing “Resource #XX” that you don’t need (leave the “Days Remaining” row)
4. Optional: If your team does not change members often, save this as your template to use for future burn downs
5. Switch to the 5th worksheet, “Sprint Information”, and enter the length of your sprint in days into cell B1 (the template will accommodate sprints of up to 100 days in length)
6. Switch to the 3rd worksheet, “Burn Down”, and you will notice that the worksheet has already been filled out with headings for your “Stand Up” day and “Days Remaining” (the same thing has also happened on the “Resource Allocation” worksheet
7. Enter the sprint tasks in column B and their initial estimates from your product backlog into “Stand Up #1” (column G). Note: The Owner cells “grey” when you enter the initial estimate. This is to remind you to fill in an owner for that task (which is the next step).
8. Select the greyed Owner cells and choose the person that agreed to take on that task from the drop down list (This list is dynamically driven from the names you entered in step #2. They appear in the same order as on that worksheet, which is why the alpha sort is useful)
Important! – There should not be any blank cells between tasks on “Burn Down”. If you need to indicate sub-tasks, use indentation and/or the “Priority” column to indicate this. You can see examples of both in Sample.xls.
That’s it! From there on all that need be done after/during a Stand Up is fill out the days remaining for any given task in the “Burn Down” worksheet. The Burn Down Chart will automatically update and the “Resource Allocation” worksheet will update to let you quickly see who (if anyone) is over or under allocated during each day of the sprint.
That covers the basics, but if you’d like to see more then open up Sample.xls.
As soon as you open it you can see from the red and green formatting what resources are over or under allocated on any given day during a sprint. The template offers tools to help manage this either by switching the Owner from the drop down list on the “Burn Down” worksheet (assuming the sprint hasn’t started), or postponing a task (assuming mid-sprint).
To postpone a task for a later sprint, switch over to the “Burn Down” sheet, and click the “+” sign over column G (it will change to a “-“ sign). This will expand some columns so you can track additional information each task (deliverable, bug id, and postponed). If you select a cell in the “Postponed” column (column F), you can choose from a drop down list to postpone a task. If you choose “Yes”, the formatting for the task name and tracking cells for that task will change so you can easily see what’s been postponed, even after collapsing the columns.
For a Release Burn Down, click on the "Release Burn Down" tab. Basically all you need do is fill in the Progress column (it will track up to 52 sprints – i.e. row 53) and the rest of it just fills in - including dynamic charting with trend lines (you need at least 2 values in the Progress column to get the chart). Two other niceties: (1) If Scope Change does occur, that column can just be filled out with the extra points, it doesn’t have to be made negative (but it will auto-correct if entered as a negative) and (2) The sprint that the trend lines indicate will allow for the release is dynamically updated in the chart legend.
*******NOTES FOR ALLOCATIONS LESS THAN 100%
If person on your team is allocated less than 100% to the sprint being tracked, you can enter their percentage of allocation in column A of the "Resource Allocation" worksheet labeled "utilization" (click on the plus sign over column B to see column A). The "Resource Allocation" worksheet will then automatically present a "normalized" view of that person's tasks (e.g. if the person is 50% allocated they are assigned 5 days of tasks on the "Burndown" sheet for a 10 day sprint, they will appear as fully utilized).
But rather than make the Scrum Master do a bunch of math (e.g. Thom is 33% allocated and only has 2.5 days of tasks left in this sprint but there are 8 days left in the sprint. How much can Thom help Amy who had to revise her estimates up in today's standup?), the Scrum Master, or anyone else for that matter, can look in the "Actual Allocation" worksheet to quickly see what that person's current actual over/under utilization is.
*******END NOTES FOR ALLOCATION LESS THAN 100%
One last thing, because the template does so much dynamically you will always be prompted to save your changes in workbooks based on it – even if you haven’t actually made any changes.
This template has helped me a lot and I hope you’ll find it useful too. Please feel free to send me any feedback to clayv at emailxtreme dot com.
- Clay
P.S. The template is not protected, so you can see how everything is done. It makes extensive use of conditional formatting, array formulas, and named ranges.